## Summary
UC1 — Multi-Step Discovery Orchestration
WBS, Estimates & Staffing — engagement summary
Companion to UC1-Solution-Implementation-Plan.md & UC1-Solution-Design.md. Estimate model & rates grounded in the attached FY25 IS template (WBS_Estimates_Staffing.xlsx).
Engagement at a glance
Total effort (hours) | 11190
Professional fees (USD) | 2922700
Total investment incl. risk reserve + expenses (USD) | 3214970
Blended rate (USD/hr) | 261.1886
Duration | ~15 months (5 phases)
Named delivery roles | 17
By workstream
Workstream | Hours | Fees (USD) | % Fees
1. Governance & Program Mgmt | 1050 | 288200 | 9.861%
2. Security & Compliance | 1040 | 278200 | 9.519%
3. Data Foundation | 2940 | 629500 | 21.54%
4. Agentic AI Discovery UC | 5600 | 1676400 | 57.36%
5. SecureByDefault & Ops | 560 | 50400 | 1.724%
Total | 11190 | 2922700 | 100%
By delivery phase
Phase | Window | Weeks | Hours | Fees (USD) | Peak FTE
P0 Foundation | Mo 0-3 | 13 | 1530 | 392040 | 2.9423
P1 Pilot | Mo 3-6 | 13 | 2170 | 606440 | 4.1731
P2 Orchestration | Mo 6-9 | 13 | 2410 | 669040 | 4.6346
P3 Federation | Mo 9-11 | 9 | 1950 | 503820 | 5.4167
P4 Scale | Mo 11-15 | 17 | 3130 | 751360 | 4.6029
Total |  | 65 | 11190 | 2922700 | 5.4167
Key assumptions & grounding
• Estimate model, role taxonomy, rate basis (Americas List Rate), 7% risk reserve and 3% reimbursable expenses follow the attached FY25 IS template (WBS_Estimates_Staffing.xlsx, sheets 'V7-1 usecase' / 'v13 with RR').
• Phases map 1:1 to UC1-Solution-Implementation-Plan.md: P0 Foundation, P1 Pilot, P2 Orchestration, P3 Federation, P4 Scale (~15 months).
• Hours are a bottom-up planning estimate (blue inputs) and must be validated with the customer (cf. deck slide 6, 'Assumptions vs Facts vs Must-Validate').
• Heavy offshore (GD Offshore @ $90) mix lowers blended rate; OCTO data-science & PG (CAPE) support assumed no-charge per template and excluded from fees.
• Excludes Azure consumption (HPC/Batch/Quantum Elements/Foundry), partner-model licensing (Gemini/Protillion/Variational) and Merck internal labour.

## Rate Card (Americas)
UC1 Rate Card — Americas List Rates (extract)
Source: FY25 IS Rate Card (attached WBS_Estimates_Staffing.xlsx → 'Ratecard', Americas List Rate, col K). Release 07/16/2024.
Resource Title | Service Line | List Rate (USD/hr)
Delivery Management Executive | Program Director | 460
Senior Project Manager | Project Management | 370
Domain Solution Architect | Delivery Consulting | 405
Senior Domain Solution Architect | Delivery Consulting | 475
Consulting Product Manager | Delivery Consulting | 355
Senior Consultant | Delivery Consulting | 365
Senior Data Scientist | Delivery Consulting | 400
Principal Data Scientist | Delivery Consulting | 500
Security Architect | Security | 445
GD Offshore | Global Delivery (offshore) | 90

## WBS & Estimates
UC1 — Multi-Step Discovery Orchestration · WBS & Estimates
Effort estimate by workstream, role and delivery phase. Hours are inputs (blue); rates link to the Rate Card (green); fees & totals are formulas (black). Currency: USD.
# | Workstream | Activity / Deliverable | Team | Project Role | Resource Title | Service | List Rate (USD) | Revenue (USD) | Total Hours | % Hours | P0 Foundation | P1 Pilot | P2 Orchestration | P3 Federation | P4 Scale
[11 empty] | Mo 0-3 | Mo 3-6 | Mo 6-9 | Mo 9-11 | Mo 11-15
1 | 1. Governance & Program Mgmt | Engagement governance, gates G0-G4, status & risk | Onshore | Delivery Management Exec | Delivery Management Executive | Program Director | 460 | 59800 | 130 | 1.162% | 26 | 26 | 26 | 18 | 34
2 | 1. Governance & Program Mgmt | Planning, sprint cadence, RAID, stakeholder mgmt | Onshore | Engagement / Project Manager | Senior Project Manager | Project Management | 370 | 192400 | 520 | 4.647% | 104 | 104 | 104 | 72 | 136
3 | 1. Governance & Program Mgmt | PMO support, reporting, logistics | Offshore | Offshore Project Manager | GD Offshore | Project Management | 90 | 36000 | 400 | 3.575% | 80 | 80 | 80 | 40 | 120
4 | 2. Security & Compliance | Annex 22 / Part 11 / ALCOA+ control design; HITL four-eyes | Onshore | Security & Compliance Architect | Security Architect | Security | 445 | 231400 | 520 | 4.647% | 160 | 120 | 80 | 80 | 80
5 | 2. Security & Compliance | Validation evidence, audit-trail config, perf-equivalence | Offshore | Compliance / Validation Consultant | GD Offshore | Security | 90 | 46800 | 520 | 4.647% | 120 | 120 | 80 | 80 | 120
6 | 3. Data Foundation | Fabric/OneLake shortcuts (S3+GCS), AHDS, AI Search, Purview lineage | Onshore | Data & AI Architect | Domain Solution Architect | Delivery Consulting | 405 | 186300 | 460 | 4.111% | 160 | 80 | 80 | 60 | 80
7 | 3. Data Foundation | Data pipelines, indexing, lineage instrumentation | Onshore | Data & AI Engineer | Senior Consultant | Delivery Consulting | 365 | 292000 | 800 | 7.149% | 240 | 160 | 120 | 120 | 160
8 | 3. Data Foundation | Build/operate data foundation (offshore) | Offshore | Data & AI Engineer (offshore) | GD Offshore | Delivery Consulting | 90 | 100800 | 1120 | 10.01% | 320 | 240 | 160 | 160 | 240
9 | 3. Data Foundation | Landing zone, networking, private endpoints (offshore) | Offshore | Azure Infra & Networking Eng (offshore) | GD Offshore | Delivery Consulting | 90 | 50400 | 560 | 5.004% | 200 | 80 | 80 | 80 | 120
10 | 4. Agentic AI Discovery UC | 5-agent pipeline & HITL gate architecture (Foundry Agent Service) | Onshore | Lead Solution Architect | Senior Domain Solution Architect | Delivery Consulting | 475 | 285000 | 600 | 5.362% | 40 | 120 | 160 | 120 | 160
11 | 4. Agentic AI Discovery UC | Use-case backlog, eval criteria, human-gate UX | Onshore | Product Owner | Consulting Product Manager | Delivery Consulting | 355 | 170400 | 480 | 4.29% | 40 | 120 | 120 | 80 | 120
12 | 4. Agentic AI Discovery UC | Model strategy: ESM/AF3/Boltz-2/RFdiffusion; triage scoring | Onshore | Principal Data Scientist | Principal Data Scientist | Delivery Consulting | 500 | 340000 | 680 | 6.077% | 40 | 160 | 200 | 120 | 160
13 | 4. Agentic AI Discovery UC | Generative design, docking, in-silico triage models | Onshore | Senior Data Scientist | Senior Data Scientist | Delivery Consulting | 400 | 336000 | 840 | 7.507% | 0 | 200 | 240 | 160 | 240
14 | 4. Agentic AI Discovery UC | Agent orchestration, A2A/MCP, custom tools & endpoints | Onshore | Data & AI Engineer (agents) | Senior Consultant | Delivery Consulting | 365 | 365000 | 1000 | 8.937% | 0 | 200 | 280 | 200 | 320
15 | 4. Agentic AI Discovery UC | Agent build & integration (offshore) | Offshore | Data & AI Engineer (offshore, agents) | GD Offshore | Delivery Consulting | 90 | 122400 | 1360 | 12.15% | 0 | 240 | 360 | 280 | 480
16 | 4. Agentic AI Discovery UC | Automated evaluation framework & regression testing | Offshore | Eval / Test Consultant (offshore) | GD Offshore | Delivery Consulting | 90 | 57600 | 640 | 5.719% | 0 | 80 | 160 | 160 | 240
17 | 5. SecureByDefault & Ops | Secure-by-default hardening, run-book, portfolio scale ops | Offshore | SbD / Platform Ops (offshore) | GD Offshore | SbD | 90 | 50400 | 560 | 5.004% | 0 | 40 | 80 | 120 | 320
| TOTAL — Professional Fees | [6 empty] | 2922700 | 11190 | 100% | 1530 | 2170 | 2410 | 1950 | 3130
Build-up to Total Investment
[7 empty] | Professional fees (subtotal) | 2922700
[7 empty] | Risk reserve % | 7% |  | Input (template default 7%)
[7 empty] | Reimbursable expenses % | 3% |  | Input (template default 3%)
[7 empty] | + Risk reserve | 204589
[7 empty] | + Reimbursable (travel) expenses | 87681
[7 empty] | TOTAL INVESTMENT (sell) | 3214970
[7 empty] | Blended rate (USD/hr) | 261.1886
Workstream rollup
| Workstream | [6 empty] | Revenue (USD) | Total Hours | % Fees
| 1. Governance & Program Mgmt | [6 empty] | 288200 | 1050 | 9.861%
| 2. Security & Compliance | [6 empty] | 278200 | 1040 | 9.519%
| 3. Data Foundation | [6 empty] | 629500 | 2940 | 21.54%
| 4. Agentic AI Discovery UC | [6 empty] | 1676400 | 5600 | 57.36%
| 5. SecureByDefault & Ops | [6 empty] | 50400 | 560 | 1.724%
| Total | [6 empty] | 2922700 | 11190 | 100%

## Staffing Plan
UC1 — Staffing Plan (FTE by phase)
FTE = phase hours ÷ (phase weeks × utilised hours/week). Hours link from WBS & Estimates (green). Weeks & hrs/week are inputs (blue).
Assumptions: | Utilised hrs/week | 40
|  | Phase weeks → | 13 | 13 | 13 | 9 | 17
Team | Project Role | Resource Title | P0 Foundation | P1 Pilot | P2 Orchestration | P3 Federation | P4 Scale | Peak FTE | Total Hours
Onshore | Delivery Management Exec | Delivery Management Executive | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 130
Onshore | Engagement / Project Manager | Senior Project Manager | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 520
Offshore | Offshore Project Manager | GD Offshore | 0.15385 | 0.15385 | 0.15385 | 0.11111 | 0.17647 | 0.17647 | 400
Onshore | Security & Compliance Architect | Security Architect | 0.30769 | 0.23077 | 0.15385 | 0.22222 | 0.11765 | 0.30769 | 520
Offshore | Compliance / Validation Consultant | GD Offshore | 0.23077 | 0.23077 | 0.15385 | 0.22222 | 0.17647 | 0.23077 | 520
Onshore | Data & AI Architect | Domain Solution Architect | 0.30769 | 0.15385 | 0.15385 | 0.16667 | 0.11765 | 0.30769 | 460
Onshore | Data & AI Engineer | Senior Consultant | 0.46154 | 0.30769 | 0.23077 | 0.33333 | 0.23529 | 0.46154 | 800
Offshore | Data & AI Engineer (offshore) | GD Offshore | 0.61538 | 0.46154 | 0.30769 | 0.44444 | 0.35294 | 0.61538 | 1120
Offshore | Azure Infra & Networking Eng (offshore) | GD Offshore | 0.38462 | 0.15385 | 0.15385 | 0.22222 | 0.17647 | 0.38462 | 560
Onshore | Lead Solution Architect | Senior Domain Solution Architect | 0.076923 | 0.23077 | 0.30769 | 0.33333 | 0.23529 | 0.33333 | 600
Onshore | Product Owner | Consulting Product Manager | 0.076923 | 0.23077 | 0.23077 | 0.22222 | 0.17647 | 0.23077 | 480
Onshore | Principal Data Scientist | Principal Data Scientist | 0.076923 | 0.30769 | 0.38462 | 0.33333 | 0.23529 | 0.38462 | 680
Onshore | Senior Data Scientist | Senior Data Scientist | 0 | 0.38462 | 0.46154 | 0.44444 | 0.35294 | 0.46154 | 840
Onshore | Data & AI Engineer (agents) | Senior Consultant | 0 | 0.38462 | 0.53846 | 0.55556 | 0.47059 | 0.55556 | 1000
Offshore | Data & AI Engineer (offshore, agents) | GD Offshore | 0 | 0.46154 | 0.69231 | 0.77778 | 0.70588 | 0.77778 | 1360
Offshore | Eval / Test Consultant (offshore) | GD Offshore | 0 | 0.15385 | 0.30769 | 0.44444 | 0.35294 | 0.44444 | 640
Offshore | SbD / Platform Ops (offshore) | GD Offshore | 0 | 0.076923 | 0.15385 | 0.33333 | 0.47059 | 0.47059 | 560
TOTAL |  | Blended FTE / phase | 2.9423 | 4.1731 | 4.6346 | 5.4167 | 4.6029 | 5.4167 | 11190
|  | Named roles (headcount) | [6 empty] | 17